## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | Co-working Space Owner | 10
1.1 | Create Co-working Space (Mongo) | 1 | Kareem ElShafey | Andrew Ashraf | Omar Hesham
1.2 | View Co-working Space attributes (Mongo) | 1 | Kareem ElShafey | Andrew Ashraf | Omar Hesham
1.3 | Update Co-working Space attributes (Mongo) | 2 | Kareem ElShafey | Andrew Ashraf | Omar Hesham
1.4 | Delete Co-working Space account (Mongo) | 1 | Kareem ElShafey | Andrew Ashraf | Omar Hesham
1.5 | I want to post new place to be booked for future events (New) | 2 | Kareem ElShafey | Andrew Ashraf | Omar Hesham
1.6 | I want to accept requests for future events (New) | 1 | Andrew Ashraf | Kareem ElShafey | Omar Hesham
1.7 | I want to mark days that I will not be able to host any events in (New) | 2 | Andrew Ashraf | Kareem ElShafey | Omar Hesham
2 | Admins | 9
2.1 | Admins System created account (Mongo) | 1 | Mohamed Sharaf | Mohamed Ibrahim | Khaled Khatar
2.2 | Edit Admins attributes (Mongo) | 1 | Mohamed Sharaf | Mohamed Ibrahim | Khaled Khatar
2.3 | Update Admins attributes (Mongo) | 2 | Mohamed Sharaf | Mohamed Ibrahim | Khaled Khatar
2.4 | Remove Delete Function for Admins as it is a system automated account cannot be Deleted (adjust) | 1 | Mohamed Sharaf | Mohamed Ibrahim | Khaled Khatar
2.5 | I want to be able to delete/hide any profile due to violations of contract or agreement. (New) | 2 | Mohamed Sharaf | Mohamed Ibrahim | Khaled Khatar
2.1 | I want to edit vacancies ad (New) | 1 | Mohamed Ibrahim | Omar Mohamed | Mohamed Sharaf
2.11 | I want to delete a vacancy ad (New) | 1 | Mohamed Ibrahim | Omar Mohamed | Mohamed Sharaf
3 | Calender | 6
3.1 | I want to create a calendar reflecting reserved places on each day (automated) (Mongo) | 2 | Andrew Ashraf | Khaled Khatar | Kareem ElShafey
3.2 | I want to view a calendar reflecting reserved places on each day (Mongo) | 1 | Andrew Ashraf | Khaled Khatar | Kareem ElShafey
3.3 | I want to set attributes to the vacancy ad so that members can see the requirements (New) | 3 | Khaled Khatar | Andrew Ashraf | Kareem ElShafey
4 | Members | 16
4.1 | Create Member account included member attributes personal info,qualifications, skills interests, past events, project tasks, jobs. (Mongo) | 1 | Omar Hesham | Adam Sadek | Youssef Samir
4.2 | Update Memeber attributes (personal info,qualifications, skills interests, past events, project tasks, jobs) (Mongo) | 1 | Omar Hesham | Adam Sadek | Youssef Samir
4.3 | View Member profile attributes (Mongo) | 2 | Adam Sadek | Omar Hesham | Youssef Samir
4.4 | Delete member account (Mongo) | 1 | Adam Sadek | Omar Hesham | Youssef Samir
4.5 | I want deactivate my account (New) | 1 | Youssef Samir | Omar Hesham | Adam Sadek
4.6 | I want to view available locations on a certain date (New) | 2 | Adam Sadek | Omar Hesham | Youssef Samir
4.7 | I want to able to request a larger area when I need to (New) | 2 | Adam Sadek | Omar Hesham | Youssef Samir
4.8 | I want to view all vacancies (New) | 1 | Youssef Samir | Omar Hesham | Adam Sadek
4.9 | I want to apply for a vacancy (New) | 1 | Youssef Samir | Omar Hesham | Adam Sadek
4.1 | I want to delete my application to a vacancy (New) | 1 | Youssef Samir | Omar Hesham | Adam Sadek
4.11 | I want to filter Vacancies according to location, salary, daily working hours, start and end duration date, owner of the ad (New) | 3 | Youssef Samir | Omar Hesham | Adam Sadek
5 | Partners | 17
5.1 | Create Partners account with attributes basic business information, partners, board members, event organized by my organization, my field of work and past projects (Mongo) | 1 | Mohamed Ibrahim | Mohamed Sharaf | Omar Mohamed
5.2 | View Partners attributes (Mongo) | 1 | Mohamed Ibrahim | Mohamed Sharaf | Omar Mohamed
5.3 | Update Partners attributes (Mongo) | 2 | Mohamed Ibrahim | Mohamed Sharaf | Omar Mohamed
5.4 | Delete Partners account basic business information, partners, board members, event organized by my organization, my field of work and past projects (Mongo) | 1 | Mohamed Ibrahim | Mohamed Sharaf | Omar Mohamed
5.5 | I want to request Vacancy ad with the description of the job (New) | 1 | Omar Mohamed | Mohamed Ibrahim | Mohamed Sharaf
5.6 | I want to be able to specify the details of my vacancy ad (New) | 2 | Omar Mohamed | Mohamed Ibrahim | Mohamed Sharaf
5.7 | I want to view the status of the vacancy ad from the moment I requested it till I decide on a candidate (New) | 1 | Omar Mohamed | Mohamed Ibrahim | Mohamed Sharaf
5.8 | I want to edit any attribute for my vacancy ad (New) | 3 | Omar Mohamed | Mohamed Ibrahim | Mohamed Sharaf
5.9 | I want to delete my vacancy ad (New) | 1 | Mohamed Refaat | Khaled Khatar | Mohamed Ibrahim
5.1 | I want to view the number of applicants who applied for my vacancy (New) | 2 | Mohamed Refaat | Khaled Khatar | Mohamed Ibrahim
5.11 | I want to be able to close my vacancy ad (New) | 1 | Mohamed Refaat | Khaled Khatar | Mohamed Ibrahim
5.12 | I want to view my old vacancy ads (New) | 1 | Mohamed Refaat | Khaled Khatar | Mohamed Ibrahim
6 | Requests | 5
6.1 | Create Requests (Mongo) | 1 | Khaled Khatar | Mohamed Refaat | Mohamed Ibrahim
6.2 | View Requests (Mongo) | 1 | Khaled Khatar | Mohamed Refaat | Mohamed Ibrahim
6.3 | Update Requests attributes (Mongo) | 2 | Mohamed Refaat | Khaled Khatar | Omar Mohamed
6.4 | Delete Requests (Mongo) | 1 | Khaled Khatar | Khaled Khatar | Omar Mohamed
7 | Vacancies | 5
7.1 | Create Vacancies (Mongo) | 1 | Omar Hesham | Andrew Ashraf | Kareem ElShafey
7.2 | View Vacancies (Mongo) | 1 | Omar Hesham | Andrew Ashraf | Kareem ElShafey
7.3 | Update Vacancies attributes (Mongo) | 2 | Omar Hesham | Andrew Ashraf | Kareem ElShafey
7.3 | Delete Vacancies (Mongo) | 1 | Omar Hesham | Andrew Ashraf | Kareem ElShafey
| SUM OF POINTS | 68