## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | Members | 4
1.1 | Create Member profile | 1 |  | Independent | Testing methods using black box
1.2 | Read Member profile | 1 |  | Independent | Testing methods using black box
1.3 | Update member profile | 1 |  | Independent | Testing methods using black box
1.4 | Delete Member profile | 1 |  | Independent | Testing methods using black box
2 | Admin | 4
2.1 | Create Admin profile | 1 |  | Independent | Testing methods using black box
2.2 | Read Admin profile | 1 |  | Independent | Testing methods using black box
2.3 | Update Admin profile | 1 |  | Independent | Testing methods using black box
2.4 | Delete Admin profile | 1 |  | Independent | Testing methods using black box
3 | Partner | 4
3.1 | Create Partner profile | 1 |  | Independent | Testing methods using black box
3.2 | Read Partner profile | 1 |  | Independent | Testing methods using black box
3.3 | Update Partner profile | 1 |  | Independent | Testing methods using black box
3.4 | Delete Partner profile | 1 |  | Independent | Testing methods using black box
4 | Request | 4
4.1 | Create Request | 1 |  | Independent | Testing methods using black box
4.2 | Read Request | 1 |  | Independent | Testing methods using black box
4.3 | Update Request | 1 |  | Independent | Testing methods using black box
4.4 | Delete Request | 1 |  | Independent | Testing methods using black box
5 | Location | 4
5.1 | Create Location | 1 |  | Independent | Testing methods using black box
5.2 | Read Location | 1 |  | Independent | Testing methods using black box
5.3 | Update Location | 1 |  | Independent | Testing methods using black box
5.4 | Delete Location | 1 |  | Independent | Testing methods using black box
6 | Vacancy | 4
6.1 | Create Vacancy | 1 |  | Independent | Testing methods using black box
6.2 | Read Vacancy | 1 |  | Independent | Testing methods using black box
6.3 | Update Vacancy | 1 |  | Independent | Testing methods using black box
6.4 | Delete Vacancy | 1 |  | Independent | Testing methods using black box
7 | Create a admin calender reflecting reserved places /autofilled by system | 5 | Andrew Ashraf | Loction Story
29 Points